## Product Backlog
Product Backlog
# | Role | Story Summary | Story Detail | Story Points | Priority | Sprint# | Status | Priority | Status | For story points we will use 1 story point = 2 hours
1 | Web Developer | Build the Technical Infrastructure | User interface, scripting, databases, functionality of the discussion board, and manage the entire web application | 11 | High | 1 | In progress | High | Not Started
2 | Web Developer | Create Website Design | Colors, logo, icons on the main page | 5 | Low | 1 | In progress | Medium | In Progess
3 | Web Developer | Create Website Functions | Functions to check users identity, track submission page, vote icons functions, payment functions | 7 | High | 1 | In progress | Low | Completed
4 | Web Developer | Determine Security Measures | Use a two-factor authentication to check identity of customers Online Verification with picture of ID | 13 | High | 4 | Not Started
5 | Administrator | Define Roles and Permissions | Admin defines roles such as "reviewers", "members", "viewers", etc. | 5 | Low | 1 | In progress
6 | Administrator | Decision Recording | Admin have the ability to make decisions on the ideas, and record the decisions made, whether it is approved, rejected, or requires further review | 3 | Medium | 1 | In progress
7 | Administrator | User Access | Admin allows and maintains access levels for members User: Read, write and execute reject, Approve, etc Print Reports | 3 | High | 2 | Not Started
8 | Administrator | Select Members | Admin has access to members informations, its background, and personal info, and can decide if member should be accepted or rejected | 3 | Medium | 3 | Not Started
9 | Visitor | Visit and see main page of the websites, and requirements to become a member | Visitor will be able to view the website and its idea, see information on how to become a member, and see summary of ideas on the website | 1 | Medium | 2 | Not Started
10 | Member | Registration/Profiles | Ability to register/ sign in to profile | 2 | High | 2 | Not Started
11 | Moderator | Keep website enviroment safe by establishing rules and guidelines | Moderator will manage forums, social platforms, discussion boards and websites | 3 | High | 4 | Not Started
12 | Member | Idea Submission | Members can submit two ideas pepr month. They have the ability to complete fields for titles, descriptions, category, etc. | 1 | High | 2 | Not Started
13 | Member | Comments and Feedback | Commenting process that allows investors to provide feedback, suggestions, and comments on submitted ideas Notifications to inform submitter of new comments or feedback | 2 | Medium | 2 | Not Started
14 | Member | Track Submission Status | Member has the ability to track their status submission, show its progress in the approval process (e.g. "Submitted", "Under Review", "Approved", "Rejected"). Ability to track when each status change occured. | 3 | Medium | 3 | Not Started
15 | Member | Revise and Re-submit Ideas | Allows members to revise and resubmit their ideas, based on feedback received | 1 | Medium | 2 | Not Started
16 | Member | Report extraction | Ability to extract in report the specific members submissions and comments | 5 | Low | 2 | Not Started
17 | Administrator | Log/Track Members Activity | Have a check box to see if members submitted two ideas per-month Vote box for rating proposals (1-10) Check if member are voting in others proposals and leaving comments If member does not post, or it has low ratings (<3), admin blocks account temporarily and user needs permission to re-join. | 5 | Medium | 2 | Not Started
18 | Administrator | Oversee Members Activity (warn/suspend/remove) | Admin must have the ability to check the users activity, the vote rating their posts are getting, and be able to warn/suspend/remove the member depedning on said activities | 7 | Medium | 2 | Not Started
19 | Member | Cancel membership | Allow user to cancel members. System will refund any prorated amount | 3 | Medium | 2 | Not Started
20 | Administrator | Check count of votes every week | Using the vote check box, the admin has the ability to count the votes each week and separate projects with higher ratings in a different folder | 3 | Low | 3 | Not Started
21 | Administrator | Select the best idea | Amin has the ability to see all the votes, rates, commments, and evrything regarding the idea and determine the top one, that will win the big prize | 3 | Medium | 3 | Not Started
22 | Administrator | Notifiy that the prize has been granted | Administrator notify the winner that the prize has been granted and confirm his/hers bank account information | 5 | Medium | 3 | Not Started
23 | Administrator | Use PLAD to verufy bank info | Admin uses PLAD (third party app) to securily verify bank account information for the winner, so the prize can be deposites | 3 | Medium | 4 | Not Started
24 | Web Developer | Create code that allows website to accept credit card | Web Developer must set up the box for credit card info, and make sure it is secure and working | 11 | High | 1 | In progress
25 | Member | Fill out credit card details for membership payments | Members need to be able to enter their credit card details on a form - card numberm name on the card, address, etc. | 5 | Medium | 4 | Not Started
26 | Administrator | Verify credit card information | Admin must be able to verify the credit card information provided, using the credit card security code | 9 | High | 4 | Not Started
27 | Administrator | Pull member information | Admin must be able to pull members information such as name, phone number, email, social security, college attended, address, etc. | 3 | Low | 2 | Not Started
29 | Web Developer | Create a code that automatically denies or accept credit card info | Web developed must develop a code that verifys credit card info. If the information is correct, accept payment, if the information is incorrect, reject payment and ask for the info again. Put a limit of 3 tries before account is blocked | 13 | High | 1 | In progress
30 | Administrator | Set up the annual date for when membership fee will be collected | Membership fee will be collected at the end of every quarter - If meber joined in Q1, membership due in March - If meber joined in Q2, membership due in June - If member joined in Q3, membership due in September - If member joined in Q4, membership due in December | 3 | Medium | 2 | Not Started
31 | Moderator | Create reminder for annual fee | Membership annual fee reminder via email 20 days prior to due date, 7 days prior, and on the due date | 1 | Low | 2 | Not Started
32 | Administrator | Handle user-related issues | Admin has the ability to handle all user related issues such as password resets, manage the account status, keep record of activity | 9 | Medium | 3 | Not Started
33 | Administrator | Manage idea users post to the website | Admin has access to a dashboard with data about user submissions, how many submissions users have made in a set period of time. Admin had the ability to dlete an idea if it violates website guidelines | 1 | Low | 3 | Not Started
34 | Administrator | Ensure security of user data | Admin utilize encryption tools, keeps the website in a secure database, and create backups of database (in case data becomes corrupted or missing) | 13 | High | 4 | Not Started
35 | Administrator | Provide interface for report generation | Admin must be able to offer report templates. Admin transfer secure data from website to generate forms. Admin controlled and verified to filter sensitive information | 9 | Low | 1 | Not Started
Use this template for the product backlog. Be sure to populate the sprint# column!
Having a sprint column allows the team to determine the feature within a sprint (spring backlog).
Use any system that the team agrees on to determine the priority. It can be numeric, or terms such as "high","medium" ,"low". it can also be another method such as "must", "should", "want" - or anything you can come up with.
Status is usually "not started","in progress" or "complete" but feel free to have your own system

## Sprint Backlog
Sprint Number | Sprint Group Definition
1 | Structure of the Website
2 | Feautures
3 | Monitor Members Activities and Ideas
4 | Security Measures
Story Summary | Sprint# | Sprint Definition
Build the Technical Infrastructure | 1 | Structure of the Website
Create Website Design | 1
Create Website Functions | 1
Define Roles and Permissions | 1
Decision Recording | 1
Create code that allows website to accept credit card | 1
Create a code that automatically denies or accept credit card info | 1
Provide interface for report generation | 1
User Access | 2 | Features
Visit and see main page of the websites, and requirements to become a member | 2
Registration/Profiles | 2
Idea Submission | 2
Comments and Feedback | 2
Revise and Re-submit Ideas | 2
Report extraction | 2
Log/Track Members Activity | 2
Oversee Members Activity (warn/suspend/remove) | 2
Cancel membership | 2
Pull member information | 2
Set up the annual date for when membership fee will be collected | 2
Create reminder for annual fee | 2
Select Members | 3 | Monitor Members Acticity and Ideas
Track Submission Status | 3
Check count of votes every week | 3
Select the best idea | 3
Notifiy that the prize has been granted | 3
Handle user-related issues | 3
Manage idea users post to the website | 3
Determine Security Measures | 4 | Security Measures
Keep website enviroment safe by establishing rules and guidelines | 4
Use PLAD to verufy bank info | 4
Fill out credit card details for membership payments | 4
Verify credit card information | 4
Ensure security of user data | 4

## Timeline
Timeline
1 story point = 2 hours
Sprint # | Story Points | Hours | Start Date | End Date | Status | Comments
1 | 64 | 128 | 2023-12-01 | 2023-12-17 | In Progress | The project will start with our web developer, that will develop all the functionalities for the website
2 | 35 | 70 | 2023-12-18 | 2023-12-26 | Not started | Admin will be working to add the features on the website, after the development is done
3 | 49 | 98 | 2023-01-01 | 2023-01-08 | Not started
4 | 36 | 72 | 2023-01-09 | 2023-01-12 | Not started | Last part of the projhect before going live is putting all security measures in place, it will be an all hands project, so we can be sure that there will be no security breach (4 resources assigned to work on security measures)
| 1 | 128 | 16 | 16 | 8
| 2 | 70 | 8.75 | 9
| 3 | 98 | 12.25 | 7
| 4 | 72 | 9 | 12 | 3
Timeline. Use this for the workshop. This is a summary timeline that only shows the timeline for each sprint. Often a project plan will have additional detail (such as task level detail), but that is more a project management issue rather than a business analyst issue.
Convert from story points to hours to estimate time.
Adjust the timeline based on the number of resources
for example, if the total story points is 30, and there are 5 hours per point, then the total hours will be 150.
If there are 2 resources assigned it will be 150/2 = 75.
We then divide the number by 8 (8 or whatever the day length is)
75/8 = 9.3 days for the sprint

## Burndown
Burndown
SPRINT 1
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16
| Remaining Effort | 128 | 120 | 110 | 100 | 87 | 80 | 72 | 65 | 60 | 51 | 45 | 38 | 27 | 19 | 10 | 5 | 0
| Baseline Effort | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
Bundown summary. Use this for the workshop. At this planning stage, it's only Possible to populate the baseline effort. The remaining effort is filled out daily as the project progresses
Base the numbers on the total sprint hours for the first sprint. Use judgement to determine how long the sprint will last based on hours. Add days (day6, day7, etc) as needed.
In agile, the number of baseline hours per day is divided up evenly over the days.
for example, if the sprint is 200 hours for 10 days, assume 10 hours are burned per day
The burndown summary shows how many hours have been burned down per day (remaining) vs. how many were projected to be burned (baseline).
This is a quick way to assess how the sprint is proceeding.
At the end of the sprint, we will see if we were over, under or on target with our hours projections.
If the team is over, they will need to address why this happened. Did we work inefficiently? Did we simply underestimate and need to up the hour per point?

## Burndown Detail
Burndown Detail
| Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Remaining Effort | 80 | 56 | 40 | 40 | 32 | 0
Baseline Effort | 80 | 64 | 48 | 32 | 16 | 0
Tasks | Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
Task 1 | 10 | 3 | 2 | 0 | 1 | 4 | 10
Task 2 | 10 | 3 | 2 | 0 | 1 | 4 | 10
Task 3 | 10 | 3 | 2 | 0 | 1 | 4 | 10
Task 4 | 10 | 3 | 2 | 0 | 1 | 4 | 10
Task 5 | 10 | 3 | 2 | 0 | 1 | 4 | 10
Task 6 | 10 | 3 | 2 | 0 | 1 | 4 | 10
Task 7 | 10 | 3 | 2 | 0 | 1 | 4 | 10
Task 8 | 10 | 3 | 2 | 0 | 1 | 4 | 10
This is included as reference only. This is not part of the workshop. we can see a detail level of tasks here, and they roll up to the summary above.

## Burndown Visual
Burndown Visual
SPRINT 1
| Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16
Remaining Effort | 128 | 120 | 110 | 100 | 87 | 80 | 72 | 65 | 60 | 51 | 45 | 38 | 27 | 19 | 10 | 5 | 0
Baseline Effort | 128 | 120 | 112 | 104 | 96 | 88 | 80 | 72 | 64 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
This chart shows how hours are actually burned (used) as opposed to how they were projected to be burned. This chart is a standard burndown chart and is included for reference only. These numbers come from the burndown detail sheet